## Sheet1
Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES
Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :-
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 |  | 001-Earth filling1 |  | 0 | 0 | 0 | 0 | 31
2 |  | avg. 0.6 m in total land area excluding golf course and ro | CU.M | 188503 | 188503 | 1 | 0 | 4 | 126 | EARTH FILLING ( AVG. 0.6 M) IN TOTAL LAND AREA EXCLUDING GO
3 |  | Plot cleaning & levelling1 | LS | 1 | 1 | 1 | 0 | 4 | 127 | PLOT CLEANING & LEVELLING

## Sheet2
Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES
Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :-
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
26 | 0 | 007-Stone masonary work |  |  |  | 0
27 | 0 | Stone masonary compound wall for plots with kiosk | Nos | 237 | 237 | 26
28 | 0 | Plot entry gate | Nos | 237 | 237 | 26
29 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 604 | 604 | 26
30 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 135 | 135 | 26
31 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 18511 | 18511 | 26
32 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 4200 | 4200 | 26
33 | 0 | Electrical / cable system |  |  |  | 0
34 | 0 | General construction electrical service - 200 KW | Lumpsum | 1 | 1 | 33
35 | 0 | Club house electrical service - 150 KW | Lumpsum | 1 | 1 | 33
36 | 0 | Electrical concealed cable work | Sqyard | 488915.8631 | 488915.8631 | 33
37 | 0 | Genset for common light 80 KVA x 5 no. | Nos | 5 | 5 | 33
38 | 0 | Electrical line shifting | Nos | 1 | 1 | 33
39 | 0 | Construction electricity bill for 5 years avg. Rs.150000/- p.m | Month | 60 | 60 | 33
40 | 0 | CC tv camera with wiring | Lumpsum | 1 | 1 | 33

## Sheet3
Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES
Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :-
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 0 | 001_Earth filling |  | 0 | 0 | 0 |  | 31
2 | 0 | avg. 0.6m in total land area excluding golf course and road | Cum | 188503 | 188503 | 1 |  | 4
3 | 0 | Plot cleaning & levelling | lumpsum | 1 | 1 | 1 |  | 4
4 | 0 | 002-Good quality earth for flower beds |  |  |  | 0 |  | 31
5 | 0 | 17.0 m wide road | Cum | 291 | 291 | 4 |  | 4
6 | 0 | 13.5 m wide road | Cum | 645 | 645 | 4 |  | 4
7 | 0 | 12.0 m wide road | Cum | 8273 | 8273 | 4 |  | 4
8 | 0 | 003-Road work |  |  |  | 0 |  | 31
9 | 0 | RW sand fill 150mm rubblesoling,100mm wetmix ex flooring | Sqft | 546135 | 546135 | 8 |  | 4
10 | 0 | 004-80 mm 4.5" x 4.5" M 30 paver block for main driveway |  |  |  | 0 |  | 31
11 | 0 | 17.0 m wide road | Sqft | 12546 | 12546 | 10 |  | 4
12 | 0 | 13.5 m wide road | Sqft | 18965 | 18965 | 10 |  | 4
13 | 0 | 12.0 m wide road | Sqft | 194584 | 194584 | 10 |  | 4
14 | 0 | 9.0 m wide road | Sqft | 118080 | 118080 | 10 |  | 4
15 | 0 | 7.5 m wide road | Sqft | 19637 | 19637 | 10 |  | 4
16 | 0 | 5.0 m wide road | Sqft | 2066 | 2066 | 10 |  | 4
17 | 0 | 005-60 mm 9" x 4.5" & 9" x 9" M 30 paver block for footpath |  |  |  | 0 |  | 31
18 | 0 | 17.0 m wide road | Sqft | 3422 | 3422 | 17 |  | 4
19 | 0 | 13.5 m wide road | Sqft | 7586 | 7586 | 17 |  | 4
20 | 0 | 12.0 m wide road | Sqft | 97292 | 97292 | 17 |  | 4
21 | 0 | 9.0 m wide road | Sqft | 59040 | 59040 | 17 |  | 4
22 | 0 | 7.5 m wide road | Sqft | 9819 | 9819 | 17 |  | 4
23 | 0 | 5.0 m wide road | Sqft | 2066 | 2066 | 17 |  | 4
24 | 0 | 006-Road cross pipe work |  |  |  | 0 |  | 31
25 | 0 | 300mm dia RCC hume pipe laying incl. excavation and filling | Nos | 80 | 80 | 24 |  | 4
26 | 0 | 007-Stone masonary work |  |  |  | 0 |  | 31
27 | 0 | Stone masonary compound wall for plots with kiosk | Nos | 237 | 237 | 26 |  | 4
28 | 0 | Plot entry gate | Nos | 237 | 237 | 26 |  | 4
29 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 604 | 604 | 26 |  | 4
30 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 135 | 135 | 26 |  | 4
31 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 18511 | 18511 | 26 |  | 4
32 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 4200 | 4200 | 26 |  | 4
33 | 0 | 008-Electrical / cable system |  |  |  | 0 |  | 31
34 | 0 | General construction electrical service - 200 KW | Lumpsum | 1 | 1 | 33 |  | 4
35 | 0 | Club house electrical service - 150 KW | Lumpsum | 1 | 1 | 33 |  | 4
36 | 0 | Electrical concealed cable work | Sqyard | 488915.8631 | 488915.8631 | 33 |  | 4
37 | 0 | Genset for common light 80 KVA x 5 no. | Nos | 5 | 5 | 33 |  | 4
38 | 0 | Electrical line shifting | Nos | 1 | 1 | 33 |  | 4
39 | 0 | Construction electricity bill for 5 years avg. Rs.150000/- p.m | Month | 60 | 60 | 33 |  | 4
40 | 0 | CC tv camera with wiring | Lumpsum | 1 | 1 | 33 |  | 4
41 | 0 | 009-Electrical poles |  |  |  | 0 |  | 31
42 | 0 | Street poles for 17.0 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4
43 | 0 | Street poles for 13.5 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4
44 | 0 | Street poles for 12.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4
45 | 0 | Street poles for 9.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4
46 | 0 | Street poles for 7.5 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4
47 | 0 | Street poles for 5.0 m road with cabling | Nos | 89.25 | 89.25 | 41 |  | 4
48 | 0 | 010-Club house |  |  |  | 0 |  | 31
49 | 0 | Club house civil work | Sqft | 45000 | 45000 | 48 |  | 4
50 | 0 | Room interior per room | Nos | 36 | 36 | 48 |  | 4
51 | 0 | Auditorium interior & equipment | Sqft | 1650.1212 | 1650.1212 | 48 |  | 4
52 | 0 | Gymnasium interior & equipment | Sqft | 1603.836 | 1603.836 | 48 |  | 4
53 | 0 | Furnitrue, a.c & equipments for other area | Sqft | 33826.0428 | 33826.0428 | 48 |  | 4
54 | 0 | CC tv & basic automation | Lumpsum | 1 | 1 | 48 |  | 4
55 | 0 | Swimming pool - Rs.35/- lit | Litres | 200000 | 200000 | 48 |  | 4
56 | 0 | Club house green area | Sqft | 7663.968 | 7663.968 | 48 |  | 4
57 | 0 | Tennis court / box cricket | Lumpsum | 1 | 1 | 48 |  | 4
58 | 0 | Club house concept design | Lumpsum | 1 | 1 | 48 |  | 4
59 | 0 | Interior design for club house | Job | 1 | 1 | 48 |  | 4
60 | 0 | UGWT | Litres | 300000 | 300000 | 48 |  | 4
61 | 0 | 250 KLD STP - 1 no. | Nos | 1 | 1 | 48 |  | 4
62 | 0 | Tube well 1 No. - 10" dia & 800 ' depth | Rft | 800 | 800 | 48 |  | 4
63 | 0 | Club house maint. For 5 years = Rs.7.5 Lacs / month | Month | 60 | 60 | 48 |  | 4
64 | 0 | Solar system | KW | 70 | 70 | 48 |  | 4
65 | 0 | 011-9 holes golf course |  |  |  | 0 |  | 31
66 | 0 | 9 holes golf course development | Acre | 19.57 | 19.57 | 65 |  | 4
67 | 0 | Golf equipment / machinery exp. | Lumpsum | 1 | 1 | 65 |  | 4
68 | 0 | Golf workshop exp. | Lumpsum | 1 | 1 | 65 |  | 4
69 | 0 | Golf cart exp. | Nos | 10 | 10 | 65 |  | 4
70 | 0 | Peripheral fabricated grill | Sqft | 14671.44 | 14671.44 | 65 |  | 4
71 | 0 | Golf maint. For 5 years = Rs.9 Lacs / month | Month | 60 | 60 | 65 |  | 4
72 | 0 | 012-Putting golf course |  |  |  | 0 |  | 31
73 | 0 | Putting golf course in zone 4 with artificial turf | Nos | 1 | 1 | 72 |  | 4
74 | 0 | Putting golf maintenance | Month | 60 | 60 | 72 |  | 4
75 | 0 | 013-Plantation and landscape work |  |  |  | 0 |  | 31
76 | 0 | Common plot development | Sqyard | 40426 | 40426 | 75 |  | 4
77 | 0 | CP-6 development in sector - D | Sqmt | 669.9814 | 669.9814 | 75 |  | 4
78 | 0 | CP-8 tennis court / box cricket in sector - E | Lumpsum | 1 | 1 | 75 |  | 4
79 | 0 | Plot internal plantation | Nos | 237 | 237 | 75 |  | 4
80 | 0 | Plot Mehndi cost | Nos | 237 | 237 | 75 |  | 4
81 | 0 | Peripherial planation | Nos | 1571 | 1571 | 75 |  | 4
82 | 0 | Plants maintenance | Sqyard | 40000 | 40000 | 75 |  | 4
83 | 0 | Cabin - 2 No. | Lumpsum | 1 | 1 | 75 |  | 4
84 | 0 | 014-Tube well 4 No. - 10" dia & 800 ' depth |  |  |  | 0 |  | 31
85 | 0 | Tube well 4 No. - 10" dia & 800 ' depth | Rft | 3200 | 3200 | 84 |  | 4
86 | 0 | 015-Ravin water harvesting |  |  |  | 0 |  | 31
87 | 0 | Recharge well | Nos | 40 | 40 | 86 |  | 4
88 | 0 | 016-Water supply system |  |  |  | 0 |  | 31
89 | 0 | Pressure systems | Nos | 6 | 6 | 88 |  | 4
90 | 0 | Water supply lines | Sqmt | 408944.4952 | 408944.4952 | 88 |  | 4
91 | 0 | UGWT | Litres | 900000 | 900000 | 88 |  | 4
92 | 0 | General drip irrigation system | Rft | 37025.952 | 37025.952 | 88 |  | 4
93 | 0 | Plot drip irrigation system | Nos | 237 | 237 | 88 |  | 4
94 | 0 | 017-Strom water drainage |  |  |  | 0 |  | 31
95 | 0 | Strom water drainage system with soakwell | Sqyard | 488916 | 488916 | 94 |  | 4
96 | 0 | 018-250 KLD STP - 2 no. |  |  |  | 0 |  | 31
97 | 0 | 250 KLD STP - 2 no. | lumpsum | 2 | 2 | 96 |  | 4

## Sheet4
Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES
Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :-
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 0 | Earth filling |  | 0 | 0 | 0 |  | 31
2 | 0 | avg. 0.6m in total land area excluding golf course and road | Cum | 188503 | 188503 | 1 |  | 4
3 | 0 | Plot cleaning & levelling | lumpsum | 1 | 1 | 1 |  | 4
4 | 0 | Good quality earth for flower beds |  |  |  | 0 |  | 31
5 | 0 | 17.0 m wide road | Cum | 291 | 291 | 4 |  | 4
6 | 0 | 13.5 m wide road | Cum | 645 | 645 | 4 |  | 4
7 | 0 | 12.0 m wide road | Cum | 8273 | 8273 | 4 |  | 4
8 | 0 | Road work |  |  |  | 0 |  | 31
9 | 0 | RW sand fill 150mm rubblesoling,100mm wetmix ex flooring | Sqft | 546135 | 546135 | 8 |  | 4
10 | 0 | 80 mm 4.5" x 4.5" M 30 paver block for main driveway |  |  |  | 0 |  | 31
11 | 0 | 17.0 m wide road | Sqft | 12546 | 12546 | 10 |  | 4
12 | 0 | 13.5 m wide road | Sqft | 18965 | 18965 | 10 |  | 4
13 | 0 | 12.0 m wide road | Sqft | 194584 | 194584 | 10 |  | 4
14 | 0 | 9.0 m wide road | Sqft | 118080 | 118080 | 10 |  | 4
15 | 0 | 7.5 m wide road | Sqft | 19637 | 19637 | 10 |  | 4
16 | 0 | 5.0 m wide road | Sqft | 2066 | 2066 | 10 |  | 4
17 | 0 | 60 mm 9" x 4.5" & 9" x 9" M 30 paver block for footpath |  |  |  | 0 |  | 31
18 | 0 | 17.0 m wide road | Sqft | 3422 | 3422 | 17 |  | 4
19 | 0 | 13.5 m wide road | Sqft | 7586 | 7586 | 17 |  | 4
20 | 0 | 12.0 m wide road | Sqft | 97292 | 97292 | 17 |  | 4
21 | 0 | 9.0 m wide road | Sqft | 59040 | 59040 | 17 |  | 4
22 | 0 | 7.5 m wide road | Sqft | 9819 | 9819 | 17 |  | 4
23 | 0 | 5.0 m wide road | Sqft | 2066 | 2066 | 17 |  | 4
24 | 0 | Road cross pipe work |  |  |  | 0 |  | 31
25 | 0 | 300mm dia RCC hume pipe laying incl. excavation and filling | Nos | 80 | 80 | 24 |  | 4
26 | 0 | Stone masonary work |  |  |  | 0 |  | 31
27 | 0 | Stone masonary compound wall for plots with kiosk | Nos | 237 | 237 | 26 |  | 4
28 | 0 | Plot entry gate | Nos | 237 | 237 | 26 |  | 4
29 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 604 | 604 | 26 |  | 4
30 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 135 | 135 | 26 |  | 4
31 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 18511 | 18511 | 26 |  | 4
32 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 4200 | 4200 | 26 |  | 4
33 | 0 | Electrical / cable system |  |  |  | 0 |  | 31
34 | 0 | General construction electrical service - 200 KW | Lumpsum | 1 | 1 | 33 |  | 4
35 | 0 | Club house electrical service - 150 KW | Lumpsum | 1 | 1 | 33 |  | 4
36 | 0 | Electrical concealed cable work | Sqyard | 488915.8631 | 488915.8631 | 33 |  | 4
37 | 0 | Genset for common light 80 KVA x 5 no. | Nos | 5 | 5 | 33 |  | 4
38 | 0 | Electrical line shifting | Nos | 1 | 1 | 33 |  | 4
39 | 0 | Construction electricity bill for 5years avg. Rs.150000/-p.m | Month | 60 | 60 | 33 |  | 4
40 | 0 | CC tv camera with wiring | Lumpsum | 1 | 1 | 33 |  | 4
41 | 0 | Electrical poles |  |  |  | 0 |  | 31
42 | 0 | Street poles for 17.0 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4
43 | 0 | Street poles for 13.5 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4
44 | 0 | Street poles for 12.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4
45 | 0 | Street poles for 9.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4
46 | 0 | Street poles for 7.5 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4
47 | 0 | Street poles for 5.0 m road with cabling | Nos | 89.25 | 89.25 | 41 |  | 4
48 | 0 | Club house |  |  |  | 0 |  | 31
49 | 0 | Club house civil work | Sqft | 45000 | 45000 | 48 |  | 4
50 | 0 | Room interior per room | Nos | 36 | 36 | 48 |  | 4
51 | 0 | Auditorium interior & equipment | Sqft | 1650.1212 | 1650.1212 | 48 |  | 4
52 | 0 | Gymnasium interior & equipment | Sqft | 1603.836 | 1603.836 | 48 |  | 4
53 | 0 | Furnitrue, a.c & equipments for other area | Sqft | 33826.0428 | 33826.0428 | 48 |  | 4
54 | 0 | CC tv & basic automation | Lumpsum | 1 | 1 | 48 |  | 4
55 | 0 | Swimming pool - Rs.35/- lit | Litres | 200000 | 200000 | 48 |  | 4
56 | 0 | Club house green area | Sqft | 7663.968 | 7663.968 | 48 |  | 4
57 | 0 | Tennis court / box cricket | Lumpsum | 1 | 1 | 48 |  | 4
58 | 0 | Club house concept design | Lumpsum | 1 | 1 | 48 |  | 4
59 | 0 | Interior design for club house | Job | 1 | 1 | 48 |  | 4
60 | 0 | UGWT | Litres | 300000 | 300000 | 48 |  | 4
61 | 0 | 250 KLD STP - 1 no. | Nos | 1 | 1 | 48 |  | 4
62 | 0 | Tube well 1 No. - 10" dia & 800 ' depth | Rft | 800 | 800 | 48 |  | 4
63 | 0 | Club house maint. For 5 years = Rs.7.5 Lacs / month | Month | 60 | 60 | 48 |  | 4
64 | 0 | Solar system | KW | 70 | 70 | 48 |  | 4
65 | 0 | 9 holes golf course |  |  |  | 0 |  | 31
66 | 0 | 9 holes golf course development | Acre | 19.57 | 19.57 | 65 |  | 4
67 | 0 | Golf equipment / machinery exp. | Lumpsum | 1 | 1 | 65 |  | 4
68 | 0 | Golf workshop exp. | Lumpsum | 1 | 1 | 65 |  | 4
69 | 0 | Golf cart exp. | Nos | 10 | 10 | 65 |  | 4
70 | 0 | Peripheral fabricated grill | Sqft | 14671.44 | 14671.44 | 65 |  | 4
71 | 0 | Golf maint. For 5 years = Rs.9 Lacs / month | Month | 60 | 60 | 65 |  | 4
72 | 0 | Putting golf course |  |  |  | 0 |  | 31
73 | 0 | Putting golf course in zone 4 with artificial turf | Nos | 1 | 1 | 72 |  | 4
74 | 0 | Putting golf maintenance | Month | 60 | 60 | 72 |  | 4
75 | 0 | Plantation and landscape work |  |  |  | 0 |  | 31
76 | 0 | Common plot development | Sqyard | 40426 | 40426 | 75 |  | 4
77 | 0 | CP-6 development in sector - D | Sqmt | 669.9814 | 669.9814 | 75 |  | 4
78 | 0 | CP-8 tennis court / box cricket in sector - E | Lumpsum | 1 | 1 | 75 |  | 4
79 | 0 | Plot internal plantation | Nos | 237 | 237 | 75 |  | 4
80 | 0 | Plot Mehndi cost | Nos | 237 | 237 | 75 |  | 4
81 | 0 | Peripherial planation | Nos | 1571 | 1571 | 75 |  | 4
82 | 0 | Plants maintenance | Sqyard | 40000 | 40000 | 75 |  | 4
83 | 0 | Cabin - 2 No. | Lumpsum | 1 | 1 | 75 |  | 4
84 | 0 | Tube well 4 No. 10" dia & 800 ' depth |  |  |  | 0 |  | 31
85 | 0 | Tube well 4 No. - 10" dia & 800 ' depth | Rft | 3200 | 3200 | 84 |  | 4
86 | 0 | Ravin water harvesting |  |  |  | 0 |  | 31
87 | 0 | Recharge well | Nos | 40 | 40 | 86 |  | 4
88 | 0 | Water supply system |  |  |  | 0 |  | 31
89 | 0 | Pressure systems | Nos | 6 | 6 | 88 |  | 4
90 | 0 | Water supply lines | Sqmt | 408944.4952 | 408944.4952 | 88 |  | 4
91 | 0 | UGWT | Litres | 900000 | 900000 | 88 |  | 4
92 | 0 | General drip irrigation system | Rft | 37025.952 | 37025.952 | 88 |  | 4
93 | 0 | Plot drip irrigation system | Nos | 237 | 237 | 88 |  | 4
94 | 0 | Strom water drainage |  |  |  | 0 |  | 31
95 | 0 | Strom water drainage system with soakwell | Sqyard | 488916 | 488916 | 94 |  | 4
96 | 0 | 250 KLD STP 2 no. |  |  |  | 0 |  | 31
97 | 0 | 250 KLD STP - 2 no. | lumpsum | 2 | 2 | 96 |  | 4

## Sheet5
Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES |  |  | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES
Selected Group :- | Selected Group :- |  |  | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :-
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] |  |  | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No |  | SR NO | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 0 |  | 1 | Earth filling |  | 0 | 0 | 0 |  | 31
2 | 0 |  | 2 | avg. 0.6m in total land area excluding golf course and road | Cum | 188503 | 188503 | 1 |  | 4 | 126
3 | 0 |  | 3 | Plot cleaning & levelling | lumpsum | 1 | 1 | 1 |  | 4 | 127
4 | 0 |  | 4 | Good quality earth for flower beds |  |  |  | 0 |  | 31
5 | 0 |  | 5 | 17.0 m wide road | Cum | 291 | 291 | 4 |  | 4 | 128
6 | 0 |  | 6 | 13.5 m wide road | Cum | 645 | 645 | 4 |  | 4 | 129
7 | 0 |  | 7 | 12.0 m wide road | Cum | 8273 | 8273 | 4 |  | 4 | 136
8 | 0 | TBC | 8 | Road work |  |  |  | 0 |  | 31
9 | 0 | TBC | 9 | RW sand fill 150mm rubblesoling,100mm wetmix ex flooring | Sqft | 546135 | 546135 | 8 |  | 4
10 | 0 |  | 10 | 80 mm 4.5" x 4.5" M 30 paver block for main driveway |  |  |  | 0 |  | 31
11 | 0 |  | 11 | 17.0 m wide road | Sqft | 12546 | 12546 | 10 |  | 4 | 46
12 | 0 |  | 12 | 13.5 m wide road | Sqft | 18965 | 18965 | 10 |  | 4 | 47
13 | 0 |  | 13 | 12.0 m wide road | Sqft | 194584 | 194584 | 10 |  | 4 | 48
14 | 0 |  | 14 | 9.0 m wide road | Sqft | 118080 | 118080 | 10 |  | 4 | 49
15 | 0 |  | 15 | 7.5 m wide road | Sqft | 19637 | 19637 | 10 |  | 4 | 50
16 | 0 |  | 16 | 5.0 m wide road | Sqft | 2066 | 2066 | 10 |  | 4 | 51
17 | 0 |  | 17 | 60 mm 9" x 4.5" & 9" x 9" M 30 paver block for footpath |  |  |  | 0 |  | 31
18 | 0 |  | 18 | 17.0 m wide road | Sqft | 3422 | 3422 | 17 |  | 4 | 52
19 | 0 |  | 19 | 13.5 m wide road | Sqft | 7586 | 7586 | 17 |  | 4 | 53
20 | 0 |  | 20 | 12.0 m wide road | Sqft | 97292 | 97292 | 17 |  | 4 | 54
21 | 0 |  | 21 | 9.0 m wide road | Sqft | 59040 | 59040 | 17 |  | 4 | 55
22 | 0 |  | 22 | 7.5 m wide road | Sqft | 9819 | 9819 | 17 |  | 4 | 56
23 | 0 |  | 23 | 5.0 m wide road | Sqft | 2066 | 2066 | 17 |  | 4 | 57
24 | 0 |  | 24 | Road cross pipe work |  |  |  | 0 |  | 31
25 | 0 |  | 25 | 300mm dia RCC hume pipe laying incl. excavation and filling | Nos | 80 | 80 | 24 |  | 4 | 29
26 | 0 | TBC | 26 | Stone masonary work |  |  |  | 0 |  | 31
27 | 0 | TBC | 27 | Stone masonary compound wall for plots with kiosk | Nos | 237 | 237 | 26 |  | 4
28 | 0 | TBC | 28 | Plot entry gate | Nos | 237 | 237 | 26 |  | 4
29 | 0 | TBC | 29 | Peripheral compound wall 6' height stone masonary | Rft | 604 | 604 | 26 |  | 4
30 | 0 | TBC | 30 | Peripheral compound wall 6' height stone masonary | Rft | 135 | 135 | 26 |  | 4
31 | 0 | TBC | 31 | Peripheral compound wall 6' height stone masonary | Rft | 18511 | 18511 | 26 |  | 4
32 | 0 | TBC | 32 | Peripheral compound wall 6' height stone masonary | Rft | 4200 | 4200 | 26 |  | 4
33 | 0 |  | 33 | Electrical / cable system |  |  |  | 0 |  | 31
34 | 0 |  | 34 | General construction electrical service - 200 KW | Lumpsum | 1 | 1 | 33 |  | 4 | 38
35 | 0 |  | 35 | Club house electrical service - 150 KW | Lumpsum | 1 | 1 | 33 |  | 4 | 39
36 | 0 |  | 36 | Electrical concealed cable work | Sqyard | 488915.8631 | 488915.8631 | 33 |  | 4 | 40
37 | 0 |  | 37 | Genset for common light 80 KVA x 5 no. | Nos | 5 | 5 | 33 |  | 4 | 41
38 | 0 |  | 38 | Electrical line shifting | Nos | 1 | 1 | 33 |  | 4 | 42
39 | 0 |  | 39 | Construction electricity bill for 5 years avg. Rs.150000/- p.m | Month | 60 | 60 | 33 |  | 4 | 43
40 | 0 |  | 40 | CC tv camera with wiring | Lumpsum | 1 | 1 | 33 |  | 4 | 44
41 | 0 |  | 41 | Electrical poles |  |  |  | 0 |  | 31
42 | 0 |  | 42 | Street poles for 17.0 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4 | 32
43 | 0 |  | 43 | Street poles for 13.5 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4 | 33
44 | 0 |  | 44 | Street poles for 12.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4 | 34
45 | 0 |  | 45 | Street poles for 9.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4 | 35
46 | 0 |  | 46 | Street poles for 7.5 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4 | 36
47 | 0 |  | 47 | Street poles for 5.0 m road with cabling | Nos | 89.25 | 89.25 | 41 |  | 4 | 37
48 | 0 |  | 48 | Club house |  |  |  | 0 |  | 31
49 | 0 |  | 49 | Club house civil work | Sqft | 45000 | 45000 | 48 |  | 4 | 145
50 | 0 |  | 50 | Room interior per room | Nos | 36 | 36 | 48 |  | 4 | 146
51 | 0 |  | 51 | Auditorium interior & equipment | Sqft | 1650.1212 | 1650.1212 | 48 |  | 4 | 147
52 | 0 |  | 52 | Gymnasium interior & equipment | Sqft | 1603.836 | 1603.836 | 48 |  | 4 | 148
53 | 0 |  | 53 | Furnitrue, a.c & equipments for other area | Sqft | 33826.0428 | 33826.0428 | 48 |  | 4 | 149
54 | 0 |  | 54 | CC tv & basic automation | Lumpsum | 1 | 1 | 48 |  | 4 | 150
55 | 0 |  | 55 | Swimming pool - Rs.35/- lit | Litres | 200000 | 200000 | 48 |  | 4 | 151
56 | 0 |  | 56 | Club house green area | Sqft | 7663.968 | 7663.968 | 48 |  | 4 | 152
57 | 0 |  | 57 | Tennis court / box cricket | Lumpsum | 1 | 1 | 48 |  | 4 | 153
58 | 0 |  | 58 | Club house concept design | Lumpsum | 1 | 1 | 48 |  | 4 | 154
59 | 0 |  | 59 | Interior design for club house | Job | 1 | 1 | 48 |  | 4 | 155
60 | 0 |  | 60 | UGWT | Litres | 300000 | 300000 | 48 |  | 4 | 156
61 | 0 |  | 61 | 250 KLD STP - 1 no. | Nos | 1 | 1 | 48 |  | 4 | 157
62 | 0 |  | 62 | Tube well 1 No. - 10" dia & 800 ' depth | Rft | 800 | 800 | 48 |  | 4 | 158
63 | 0 |  | 63 | Club house maint. For 5 years = Rs.7.5 Lacs / month | Month | 60 | 60 | 48 |  | 4 | 159
64 | 0 |  | 64 | Solar system | KW | 70 | 70 | 48 |  | 4 | 160
65 | 0 |  | 65 | 9 holes golf course |  |  |  | 0 |  | 31
66 | 0 | TBC | 66 | 9 holes golf course development | Acre | 19.57 | 19.57 | 65 |  | 4
67 | 0 | TBC | 67 | Golf equipment / machinery exp. | Lumpsum | 1 | 1 | 65 |  | 4
68 | 0 | TBC | 68 | Golf workshop exp. | Lumpsum | 1 | 1 | 65 |  | 4
69 | 0 | TBC | 69 | Golf cart exp. | Nos | 10 | 10 | 65 |  | 4
70 | 0 | TBC | 70 | Peripheral fabricated grill | Sqft | 14671.44 | 14671.44 | 65 |  | 4
71 | 0 | TBC | 71 | Golf maint. For 5 years = Rs.9 Lacs / month | Month | 60 | 60 | 65 |  | 4
72 | 0 | TBC | 72 | Putting golf course |  |  |  | 0 |  | 31
73 | 0 | TBC | 73 | Putting golf course in zone 4 with artificial turf | Nos | 1 | 1 | 72 |  | 4
74 | 0 | TBC | 74 | Putting golf maintenance | Month | 60 | 60 | 72 |  | 4
75 | 0 | TBC | 75 | Plantation and landscape work |  |  |  | 0 |  | 31
76 | 0 | TBC | 76 | Common plot development | Sqyard | 40426 | 40426 | 75 |  | 4
77 | 0 | TBC | 77 | CP-6 development in sector - D | Sqmt | 669.9814 | 669.9814 | 75 |  | 4
78 | 0 | TBC | 78 | CP-8 tennis court / box cricket in sector - E | Lumpsum | 1 | 1 | 75 |  | 4
79 | 0 | TBC | 79 | Plot internal plantation | Nos | 237 | 237 | 75 |  | 4
80 | 0 | TBC | 80 | Plot Mehndi cost | Nos | 237 | 237 | 75 |  | 4
81 | 0 | TBC | 81 | Peripherial planation | Nos | 1571 | 1571 | 75 |  | 4
82 | 0 | TBC | 82 | Plants maintenance | Sqyard | 40000 | 40000 | 75 |  | 4
83 | 0 | TBC | 83 | Cabin - 2 No. | Lumpsum | 1 | 1 | 75 |  | 4
84 | 0 | TBC | 84 | Tube well 4 No. 10" dia & 800 ' depth |  |  |  | 0 |  | 31
85 | 0 | TBC | 85 | Tube well 4 No. - 10" dia & 800 ' depth | Rft | 3200 | 3200 | 84 |  | 4
86 | 0 | TBC | 86 | Rain water harvesting |  |  |  | 0 |  | 31
87 | 0 | TBC | 87 | Recharge well | Nos | 40 | 40 | 86 |  | 4
88 | 0 | TBC | 88 | Water supply system |  |  |  | 0 |  | 31
89 | 0 | TBC | 89 | Pressure systems | Nos | 6 | 6 | 88 |  | 4
90 | 0 | TBC | 90 | Water supply lines | Sqmt | 408944.4952 | 408944.4952 | 88 |  | 4
91 | 0 | TBC | 91 | UGWT | Litres | 900000 | 900000 | 88 |  | 4
92 | 0 | TBC | 92 | General drip irrigation system | Rft | 37025.952 | 37025.952 | 88 |  | 4
93 | 0 | TBC | 93 | Plot drip irrigation system | Nos | 237 | 237 | 88 |  | 4
94 | 0 | TBC | 94 | Strom water drainage |  |  |  | 0 |  | 31
95 | 0 | TBC | 95 | Strom water drainage system with soakwell | Sqyard | 488916 | 488916 | 94 |  | 4
96 | 0 | TBC | 96 | 250 KLD STP 2 no. |  |  |  | 0 |  | 31
97 | 0 | TBC | 97 | 250 KLD STP - 2 no. | lumpsum | 2 | 2 | 96 |  | 4

## Sheet6
Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES | Project :-SYLVAN GOLF & COUNTRY HOMES
Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :- | Selected Group :-
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 0 | Earth filling |  | 0 | 0 | 0 |  | 31
2 | 0 | avg. 0.6m in total land area excluding golf course and road | Cum | 188503 | 188503 | 1 |  | 4 | 126
3 | 0 | Plot cleaning & levelling | lumpsum | 1 | 1 | 1 |  | 4 | 127
4 | 0 | Good quality earth for flower beds |  |  |  | 0 |  | 31
5 | 0 | 17.0 m wide road | Cum | 291 | 291 | 4 |  | 4 | 128
6 | 0 | 13.5 m wide road | Cum | 645 | 645 | 4 |  | 4 | 129
7 | 0 | 12.0 m wide road | Cum | 8273 | 8273 | 4 |  | 4 | 136
8 | 0 | Road work |  |  |  | 0 |  | 31
9 | 0 | RW sand fill 150mm rubblesoling,100mm wetmix ex flooring | Sqft | 546135 | 546135 | 8 |  | 4
10 | 0 | 80 mm 4.5" x 4.5" M 30 paver block for main driveway |  |  |  | 0 |  | 31
11 | 0 | 17.0 m wide road | Sqft | 12546 | 12546 | 10 |  | 4 | 46
12 | 0 | 13.5 m wide road | Sqft | 18965 | 18965 | 10 |  | 4 | 47
13 | 0 | 12.0 m wide road | Sqft | 194584 | 194584 | 10 |  | 4 | 48
14 | 0 | 9.0 m wide road | Sqft | 118080 | 118080 | 10 |  | 4 | 49
15 | 0 | 7.5 m wide road | Sqft | 19637 | 19637 | 10 |  | 4 | 50
16 | 0 | 5.0 m wide road | Sqft | 2066 | 2066 | 10 |  | 4 | 51
17 | 0 | 60 mm 9" x 4.5" & 9" x 9" M 30 paver block for footpath |  |  |  | 0 |  | 31
18 | 0 | 17.0 m wide road | Sqft | 3422 | 3422 | 17 |  | 4 | 52
19 | 0 | 13.5 m wide road | Sqft | 7586 | 7586 | 17 |  | 4 | 53
20 | 0 | 12.0 m wide road | Sqft | 97292 | 97292 | 17 |  | 4 | 54
21 | 0 | 9.0 m wide road | Sqft | 59040 | 59040 | 17 |  | 4 | 55
22 | 0 | 7.5 m wide road | Sqft | 9819 | 9819 | 17 |  | 4 | 56
23 | 0 | 5.0 m wide road | Sqft | 2066 | 2066 | 17 |  | 4 | 57
24 | 0 | Road cross pipe work |  |  |  | 0 |  | 31
25 | 0 | 300mm dia RCC hume pipe laying incl. excavation and filling | Nos | 80 | 80 | 24 |  | 4 | 29
26 | 0 | Stone masonary work |  |  |  | 0 |  | 31
27 | 0 | Stone masonary compound wall for plots with kiosk | Nos | 237 | 237 | 26 |  | 4
28 | 0 | Plot entry gate | Nos | 237 | 237 | 26 |  | 4
29 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 604 | 604 | 26 |  | 4
30 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 135 | 135 | 26 |  | 4
31 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 18511 | 18511 | 26 |  | 4
32 | 0 | Peripheral compound wall 6' height stone masonary | Rft | 4200 | 4200 | 26 |  | 4
33 | 0 | Electrical / cable system |  |  |  | 0 |  | 31
34 | 0 | General construction electrical service - 200 KW | Lumpsum | 1 | 1 | 33 |  | 4 | 38
35 | 0 | Club house electrical service - 150 KW | Lumpsum | 1 | 1 | 33 |  | 4 | 39
36 | 0 | Electrical concealed cable work | Sqyard | 488915.8631 | 488915.8631 | 33 |  | 4 | 40
37 | 0 | Genset for common light 80 KVA x 5 no. | Nos | 5 | 5 | 33 |  | 4 | 41
38 | 0 | Electrical line shifting | Nos | 1 | 1 | 33 |  | 4 | 42
39 | 0 | Construction electricity bill for 5years avg. Rs.150000 p.m | Month | 60 | 60 | 33 |  | 4 | 43
40 | 0 | CC tv camera with wiring | Lumpsum | 1 | 1 | 33 |  | 4 | 44
41 | 0 | Electrical poles |  |  |  | 0 |  | 31
42 | 0 | Street poles for 17.0 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4 | 32
43 | 0 | Street poles for 13.5 m road with cabling | Nos | 47.035 | 47.035 | 41 |  | 4 | 33
44 | 0 | Street poles for 12.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4 | 34
45 | 0 | Street poles for 9.0 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4 | 35
46 | 0 | Street poles for 7.5 m road with cabling | Nos | 32.25 | 32.25 | 41 |  | 4 | 36
47 | 0 | Street poles for 5.0 m road with cabling | Nos | 89.25 | 89.25 | 41 |  | 4 | 37
48 | 0 | Club house |  |  |  | 0 |  | 31
49 | 0 | Club house civil work | Sqft | 45000 | 45000 | 48 |  | 4 | 145
50 | 0 | Room interior per room | Nos | 36 | 36 | 48 |  | 4 | 146
51 | 0 | Auditorium interior & equipment | Sqft | 1650.1212 | 1650.1212 | 48 |  | 4 | 147
52 | 0 | Gymnasium interior & equipment | Sqft | 1603.836 | 1603.836 | 48 |  | 4 | 148
53 | 0 | Furnitrue, a.c & equipments for other area | Sqft | 33826.0428 | 33826.0428 | 48 |  | 4 | 149
54 | 0 | CC tv & basic automation | Lumpsum | 1 | 1 | 48 |  | 4 | 150
55 | 0 | Swimming pool - Rs.35/- lit | Litres | 200000 | 200000 | 48 |  | 4 | 151
56 | 0 | Club house green area | Sqft | 7663.968 | 7663.968 | 48 |  | 4 | 152
57 | 0 | Tennis court / box cricket | Lumpsum | 1 | 1 | 48 |  | 4 | 153
58 | 0 | Club house concept design | Lumpsum | 1 | 1 | 48 |  | 4 | 154
59 | 0 | Interior design for club house | Job | 1 | 1 | 48 |  | 4 | 155
60 | 0 | UGWT | Litres | 300000 | 300000 | 48 |  | 4 | 156
61 | 0 | 250 KLD STP - 1 no. | Nos | 1 | 1 | 48 |  | 4 | 157
62 | 0 | Tube well 1 No. - 10" dia & 800 ' depth | Rft | 800 | 800 | 48 |  | 4 | 158
63 | 0 | Club house maint. For 5 years = Rs.7.5 Lacs / month | Month | 60 | 60 | 48 |  | 4 | 159
64 | 0 | Solar system | KW | 70 | 70 | 48 |  | 4 | 160
65 | 0 | 9 holes golf course |  |  |  | 0 |  | 31
66 | 0 | 9 holes golf course development | Acre | 19.57 | 19.57 | 65 |  | 4
67 | 0 | Golf equipment / machinery exp. | Lumpsum | 1 | 1 | 65 |  | 4
68 | 0 | Golf workshop exp. | Lumpsum | 1 | 1 | 65 |  | 4
69 | 0 | Golf cart exp. | Nos | 10 | 10 | 65 |  | 4
70 | 0 | Peripheral fabricated grill | Sqft | 14671.44 | 14671.44 | 65 |  | 4
71 | 0 | Golf maint. For 5 years = Rs.9 Lacs / month | Month | 60 | 60 | 65 |  | 4
72 | 0 | Putting golf course |  |  |  | 0 |  | 31
73 | 0 | Putting golf course in zone 4 with artificial turf | Nos | 1 | 1 | 72 |  | 4
74 | 0 | Putting golf maintenance | Month | 60 | 60 | 72 |  | 4
75 | 0 | Plantation and landscape work |  |  |  | 0 |  | 31
76 | 0 | Common plot development | Sqyard | 40426 | 40426 | 75 |  | 4
77 | 0 | CP-6 development in sector - D | Sqmt | 669.9814 | 669.9814 | 75 |  | 4
78 | 0 | CP-8 tennis court / box cricket in sector - E | Lumpsum | 1 | 1 | 75 |  | 4
79 | 0 | Plot internal plantation | Nos | 237 | 237 | 75 |  | 4
80 | 0 | Plot Mehndi cost | Nos | 237 | 237 | 75 |  | 4
81 | 0 | Peripherial planation | Nos | 1571 | 1571 | 75 |  | 4
82 | 0 | Plants maintenance | Sqyard | 40000 | 40000 | 75 |  | 4
83 | 0 | Cabin - 2 No. | Lumpsum | 1 | 1 | 75 |  | 4
84 | 0 | Tube well 4 No. 10" dia & 800 ' depth |  |  |  | 0 |  | 31
85 | 0 | Tube well 4 No. - 10" dia & 800 ' depth | Rft | 3200 | 3200 | 84 |  | 4
86 | 0 | Rain water harvesting |  |  |  | 0 |  | 31
87 | 0 | Recharge well | Nos | 40 | 40 | 86 |  | 4
88 | 0 | Water supply system |  |  |  | 0 |  | 31
89 | 0 | Pressure systems | Nos | 6 | 6 | 88 |  | 4
90 | 0 | Water supply lines | Sqmt | 408944.4952 | 408944.4952 | 88 |  | 4
91 | 0 | UGWT | Litres | 900000 | 900000 | 88 |  | 4
92 | 0 | General drip irrigation system | Rft | 37025.952 | 37025.952 | 88 |  | 4
93 | 0 | Plot drip irrigation system | Nos | 237 | 237 | 88 |  | 4
94 | 0 | Strom water drainage |  |  |  | 0 |  | 31
95 | 0 | Strom water drainage system with soakwell | Sqyard | 488916 | 488916 | 94 |  | 4
96 | 0 | 250 KLD STP 2 no. |  |  |  | 0 |  | 31
97 | 0 | 250 KLD STP - 2 no. | lumpsum | 2 | 2 | 96 |  | 4