## Sheet1
Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA | Project :-STELLA
Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 4945 | CONCRETE |  | 0.0000 | 0.0000 | 0 | 4645 | 31 | 0 | [6 empty] | 0.0000
2 | 5022 | FOUNDATION |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
3 | 5023 | FOUNDATION PCC FOR FOUNDATION M15 | CUM | 514.0000 | 514.0000 | 2 | 5022 | 4 | 3 | PCC FOR FOUNDATION M15 | [5 empty] | 0.0000
4 | 5025 | FOUNDATION PCC FOR GRADE SLAB M15 | CUM | 742.0000 | 742.0000 | 2 | 5022 | 4 | 4 | PCC FOR GRADE SLAB M15 | [5 empty] | 0.0000
5 | 5026 | FOUNDATION RETAINING WALL RW2 M30 | CUM | 2343.5300 | 2343.5300 | 2 | 5022 | 4 | 40 | RETAINING WALL RW2 M30 | [5 empty] | 0.0000
6 | 5049 | FOUNDATION PIT WALL M30 | CUM | 192.5000 | 192.5000 | 2 | 5022 | 4 | 41 | PIT WALL M30 | [5 empty] | 0.0000
7 | 5050 | FOUNDATION RETAINING WALL RW1 M30 | CUM | 350.0600 | 350.0600 | 2 | 5022 | 4 | 7 | RETAINING WALL RW1 M30 | [5 empty] | 0.0000
8 | 5051 | FOUNDATION GRADE SLAB M30 | CUM | 2652.0000 | 2652.0000 | 2 | 5022 | 4 | 6 | GRADE SLAB M30 | [5 empty] | 0.0000
9 | 5052 | FOUNDATION CONCRETE M25 | CUM | 1500.0000 | 1500.0000 | 2 | 5022 | 4 | 5 | CONCRETE M25 | [5 empty] | 0.0000
10 | 5053 | FOUNDATION OTHER RCC WALL CONCRETE FOR UGWT & OHWT | CUM | 339.7100 | 339.7100 | 2 | 5022 | 4 | 43 | OTHER RCC WALL CONCRETE FOR UGWT & OHWT | [5 empty] | 0.0000
11 | 5169 | FOUNDATION FOOTING M40 | CUM | 628.0000 | 628.0000 | 2 | 5022 | 4 | 24 | FOOTING M40 | [5 empty] | 0.0000
12 | 5170 | FOUNDATION RAFT FOUNDATION M45 | CUM | 8816.0000 | 8816.0000 | 2 | 5022 | 4 | 23 | RAFT FOUNDATION M45 | [5 empty] | 0.0000
13 | 4956 | 3B |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
14 | 5094 | 3B BEAM, SLAB, STAIR M35 | CUM | 1276.92 | 1276.92 | 13 | 4956 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
15 | 5095 | 3B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 332.2 | 332.2 | 13 | 4956 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
16 | 5096 | 3B BEAM, SLAB & STAIR M45 | CUM | 1063.77 | 1063.77 | 13 | 4956 | 4 | 16 | BEAM, SLAB & STAIR M45 | [5 empty] | 0.0000
17 | 5097 | 3B SHEAR WALL / LIFT WALL / COLUMN M60 | CUM | 758.1 | 758.1 | 13 | 4956 | 4 | 8 | SHEAR WALL / LIFT WALL / COLUMN M60 | [5 empty] | 0.0000
18 | 4957 | 2B |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
19 | 5098 | 2B BEAM, SLAB, STAIR M35 | CUM | 1008.92 | 1008.92 | 18 | 4957 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
20 | 5099 | 2B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 276.8 | 276.8 | 18 | 4957 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
21 | 5100 | 2B BEAM, SLAB & STAIR M45 | CUM | 1348.46 | 1348.46 | 18 | 4957 | 4 | 16 | BEAM, SLAB & STAIR M45 | [5 empty] | 0.0000
22 | 5101 | 2B SHEAR WALL / LIFT WALL / COLUMN M60 | CUM | 720.83 | 720.83 | 18 | 4957 | 4 | 8 | SHEAR WALL / LIFT WALL / COLUMN M60 | [5 empty] | 0.0000
23 | 4958 | 1B |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
24 | 5027 | 1B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 286.28 | 286.28 | 23 | 4958 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
25 | 5102 | 1B BEAM, SLAB, STAIR M35 | CUM | 1177.56 | 1177.56 | 23 | 4958 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
26 | 5103 | 1B BEAM, SLAB & STAIR M45 | CUM | 1162.31 | 1162.31 | 23 | 4958 | 4 | 16 | BEAM, SLAB & STAIR M45 | [5 empty] | 0.0000
27 | 5104 | 1B SHEAR WALL / LIFT WALL / COLUMN M60 | CUM | 773.94 | 773.94 | 23 | 4958 | 4 | 8 | SHEAR WALL / LIFT WALL / COLUMN M60 | [5 empty] | 0.0000
28 | 4959 | GF |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
29 | 5028 | GF SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 253.2 | 253.2 | 28 | 4959 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
30 | 5029 | GF SHEAR WALL / LIFT WALL / COLUMN M60 | CUM | 656.5400 | 656.5400 | 28 | 4959 | 4 | 8 | SHEAR WALL / LIFT WALL / COLUMN M60 | [5 empty] | 0.0000
31 | 5105 | GF BEAM, SLAB, STAIR M35 | CUM | 545.3868 | 545.3868 | 28 | 4959 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
32 | 5108 | GF BEAM, SLAB & STAIR M45 | CUM | 1013.0300 | 1013.0300 | 28 | 4959 | 4 | 16 | BEAM, SLAB & STAIR M45 | [5 empty] | 0.0000
33 | 5171 | GF GROUND FLOOR RCC WALL M30 | CUM | 347.4700 | 347.4700 | 28 | 4959 | 4 | 15 | GROUND FLOOR RCC WALL M30 | [5 empty] | 0.0000
34 | 4960 | 1F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
35 | 5114 | 1F BEAM, SLAB, STAIR M35 | CUM | 350.6200 | 350.6200 | 34 | 4960 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
36 | 5115 | 1F BEAM, SLAB & STAIR M45 | CUM | 910.2200 | 910.2200 | 34 | 4960 | 4 | 16 | BEAM, SLAB & STAIR M45 | [5 empty] | 0.0000
37 | 5116 | 1F SHEAR WALL / LIFT WALL / COLUMN M60 | CUM | 536.1200 | 536.1200 | 34 | 4960 | 4 | 8 | SHEAR WALL / LIFT WALL / COLUMN M60 | [5 empty] | 0.0000
38 | 4961 | 2F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
39 | 5117 | 2F BEAM, SLAB & STAIR M45 | CUM | 568.9400 | 568.9400 | 38 | 4961 | 4 | 16 | BEAM, SLAB & STAIR M45 | [5 empty] | 0.0000
40 | 5118 | 2F SHEAR WALL / LIFT WALL / COLUMN M60 | CUM | 389.2055 | 389.2055 | 38 | 4961 | 4 | 8 | SHEAR WALL / LIFT WALL / COLUMN M60 | [5 empty] | 0.0000
41 | 4962 | 3F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
42 | 5120 | 3F BEAM, SLAB & STAIR M40 | CUM | 682.08 | 682.08 | 41 | 4962 | 4 | 17 | BEAM, SLAB & STAIR M40 | [5 empty] | 0.0000
43 | 5121 | 3F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 343.1600 | 343.1600 | 41 | 4962 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
44 | 4964 | 4F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
45 | 5123 | 4F BEAM, SLAB & STAIR M30 | CUM | 0.0000 | 0.0000 | 44 | 4964 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
46 | 5124 | 4F BEAM, SLAB & STAIR M40 | CUM | 652.67 | 652.67 | 44 | 4964 | 4 | 17 | BEAM, SLAB & STAIR M40 | [5 empty] | 0.0000
47 | 5125 | 4F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 354.82 | 354.82 | 44 | 4964 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
48 | 4965 | 5F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
49 | 5126 | 5F BEAM, SLAB & STAIR M40 | CUM | 645.97 | 645.97 | 48 | 4965 | 4 | 17 | BEAM, SLAB & STAIR M40 | [5 empty] | 0.0000
50 | 5127 | 5F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 335.08 | 335.08 | 48 | 4965 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
51 | 4966 | 6F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
52 | 5132 | 6F BEAM, SLAB & STAIR M40 | CUM | 686.2 | 686.2 | 51 | 4966 | 4 | 17 | BEAM, SLAB & STAIR M40 | [5 empty] | 0.0000
53 | 5134 | 6F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 333 | 333 | 51 | 4966 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
54 | 4967 | 7F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
55 | 5136 | 7F BEAM, SLAB, STAIR M35 | CUM | 683.7600 | 683.7600 | 54 | 4967 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
56 | 5137 | 7F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 378.4700 | 378.4700 | 54 | 4967 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
57 | 4968 | 8F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
58 | 5138 | 8F BEAM, SLAB, STAIR M35 | CUM | 687.3100 | 687.3100 | 57 | 4968 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
59 | 5139 | 8F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 378.4700 | 378.4700 | 57 | 4968 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
60 | 4969 | 9F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
61 | 5140 | 9F BEAM, SLAB, STAIR M35 | CUM | 684.7500 | 684.7500 | 60 | 4969 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
62 | 5141 | 9F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 378.4700 | 378.4700 | 60 | 4969 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
63 | 4970 | 10F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
64 | 5142 | 10F BEAM, SLAB, STAIR M35 | CUM | 684.6400 | 684.6400 | 63 | 4970 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
65 | 5143 | 10F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 378.4700 | 378.4700 | 63 | 4970 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
66 | 4971 | 11F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
67 | 5144 | 11F BEAM, SLAB, STAIR M35 | CUM | 683.9800 | 683.9800 | 66 | 4971 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
68 | 5145 | 11F SHEAR WALL / LIFT WALL / COLUMN M45 | CUM | 362.4100 | 362.4100 | 66 | 4971 | 4 | 449 | SHEAR WALL / LIFT WALL / COLUMN M45 | [5 empty] | 0.0000
69 | 4972 | 12F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
70 | 5152 | 12F BEAM, SLAB, STAIR M35 | CUM | 688.1100 | 688.1100 | 69 | 4972 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
71 | 5153 | 12F SHEAR WALL / LIFT WALL / COLUMN M45 | CUM | 362.4100 | 362.4100 | 69 | 4972 | 4 | 449 | SHEAR WALL / LIFT WALL / COLUMN M45 | [5 empty] | 0.0000
72 | 4973 | 13F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
73 | 5154 | 13F BEAM, SLAB, STAIR M35 | CUM | 681.3100 | 681.3100 | 72 | 4973 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
74 | 5155 | 13F SHEAR WALL / LIFT WALL / COLUMN M45 | CUM | 362.4100 | 362.4100 | 72 | 4973 | 4 | 449 | SHEAR WALL / LIFT WALL / COLUMN M45 | [5 empty] | 0.0000
75 | 4974 | 14F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
76 | 5156 | 14F BEAM, SLAB, STAIR M35 | CUM | 687.3400 | 687.3400 | 75 | 4974 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
77 | 5157 | 14F SHEAR WALL / LIFT WALL / COLUMN M45 | CUM | 362.41 | 362.41 | 75 | 4974 | 4 | 449 | SHEAR WALL / LIFT WALL / COLUMN M45 | [5 empty] | 0.0000
78 | 4975 | 15F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
79 | 5158 | 15F BEAM, SLAB, STAIR M35 | CUM | 684.75 | 684.75 | 78 | 4975 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
80 | 5159 | 15F SHEAR WALL / LIFT WALL / COLUMN M45 | CUM | 362.41 | 362.41 | 78 | 4975 | 4 | 449 | SHEAR WALL / LIFT WALL / COLUMN M45 | [5 empty] | 0.0000
81 | 4976 | 16F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
82 | 5160 | 16F BEAM, SLAB, STAIR M35 | CUM | 684.64 | 684.64 | 81 | 4976 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
83 | 5161 | 16F SHEAR WALL / LIFT WALL / COLUMN M45 | CUM | 362.41 | 362.41 | 81 | 4976 | 4 | 449 | SHEAR WALL / LIFT WALL / COLUMN M45 | [5 empty] | 0.0000
84 | 4977 | 17F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
85 | 5066 | 17F BEAM, SLAB & STAIR M30 | CUM | 683.98 | 683.98 | 84 | 4977 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
86 | 5067 | 17F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 378.47 | 378.47 | 84 | 4977 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
87 | 4978 | 18F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
88 | 5068 | 18F BEAM, SLAB & STAIR M30 | CUM | 688.08 | 688.08 | 87 | 4978 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
89 | 5069 | 18F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 378.47 | 378.47 | 87 | 4978 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
90 | 4979 | 19F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
91 | 5070 | 19F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 378.47 | 378.47 | 90 | 4979 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
92 | 5071 | 19F BEAM, SLAB & STAIR M30 | CUM | 681.31 | 681.31 | 90 | 4979 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
93 | 4980 | 20F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
94 | 5072 | 20F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 378.47 | 378.47 | 93 | 4980 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
95 | 5073 | 20F BEAM, SLAB & STAIR M30 | CUM | 691.99 | 691.99 | 93 | 4980 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
96 | 4981 | 21F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
97 | 5074 | 21F BEAM, SLAB & STAIR M30 | CUM | 646.43 | 646.43 | 96 | 4981 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
98 | 5075 | 21F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 378.47 | 378.47 | 96 | 4981 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
99 | 4982 | 22F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
100 | 5076 | 22F BEAM, SLAB & STAIR M30 | CUM | 476.89 | 476.89 | 99 | 4982 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
101 | 5077 | 22F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 255.25 | 255.25 | 99 | 4982 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
102 | 4983 | 23F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
103 | 5078 | 23F BEAM, SLAB & STAIR M30 | CUM | 476.91 | 476.91 | 102 | 4983 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
104 | 5079 | 23F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 255.25 | 255.25 | 102 | 4983 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
105 | 4984 | 24F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
106 | 5080 | 24F BEAM, SLAB & STAIR M30 | CUM | 476.25 | 476.25 | 105 | 4984 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
107 | 5081 | 24F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 105 | 4984 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
108 | 4985 | 25F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
109 | 5082 | 25F BEAM, SLAB & STAIR M30 | CUM | 480.35 | 480.35 | 108 | 4985 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
110 | 5083 | 25F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 108 | 4985 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
111 | 4986 | 26F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
112 | 5084 | 26F BEAM, SLAB & STAIR M30 | CUM | 473.58 | 473.58 | 111 | 4986 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
113 | 5085 | 26F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 111 | 4986 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
114 | 4987 | 27F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
115 | 5086 | 27F BEAM, SLAB & STAIR M30 | CUM | 479.58 | 479.58 | 114 | 4987 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
116 | 5087 | 27F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 114 | 4987 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
117 | 4988 | 28F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
118 | 5088 | 28F BEAM, SLAB & STAIR M30 | CUM | 477.02 | 477.02 | 117 | 4988 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
119 | 5089 | 28F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 117 | 4988 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
120 | 4989 | 29F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
121 | 5090 | 29F BEAM, SLAB & STAIR M30 | CUM | 476.91 | 476.91 | 120 | 4989 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
122 | 5091 | 29F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 120 | 4989 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
123 | 4990 | 30F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
124 | 5092 | 30F BEAM, SLAB & STAIR M30 | CUM | 476.91 | 476.91 | 123 | 4990 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
125 | 5093 | 30F SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 239.19 | 239.19 | 123 | 4990 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000
126 | 4991 | 31F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
127 | 5055 | 31F SHEAR WALL / LIFT WALL / COLUMN M30 | CUM | 239.19 | 239.19 | 126 | 4991 | 4 | 14 | SHEAR WALL / LIFT WALL / COLUMN M30 | [5 empty] | 0.0000
128 | 5163 | 31F BEAM, SLAB & STAIR M30 | CUM | 480.35 | 480.35 | 126 | 4991 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
129 | 4992 | 32F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
130 | 5056 | 32F SHEAR WALL / LIFT WALL / COLUMN M30 | CUM | 239.19 | 239.19 | 129 | 4992 | 4 | 14 | SHEAR WALL / LIFT WALL / COLUMN M30 | [5 empty] | 0.0000
131 | 5164 | 32F BEAM, SLAB & STAIR M30 | CUM | 816.69 | 816.69 | 129 | 4992 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
132 | 4993 | 33F |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
133 | 5057 | 33F SHEAR WALL / LIFT WALL / COLUMN M30 | CUM | 0.0000 | 0.0000 | 132 | 4993 | 4 | 14 | SHEAR WALL / LIFT WALL / COLUMN M30 | [5 empty] | 0.0000
134 | 5162 | 33F BEAM, SLAB & STAIR M30 | CUM | 0.0000 | 0.0000 | 132 | 4993 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
135 | 5058 | TF |  | 0.0000 | 0.0000 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
136 | 5059 | TF SHEAR WALL / LIFT WALL / COLUMN M30 | CUM | 478.38 | 478.38 | 135 | 5058 | 4 | 14 | SHEAR WALL / LIFT WALL / COLUMN M30 | [5 empty] | 0.0000
137 | 5165 | TF BEAM, SLAB & STAIR M30 | CUM | 747.7 | 747.7 | 135 | 5058 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
138 | 5172 | TF PARAPET WALL M30 | CUM | 152.59 | 152.59 | 135 | 5058 | 4 | 22 | PARAPET WALL M30 | [5 empty] | 0.0000
139 | 5167 | LINTEL & MULLION |  | 356.03 | 356.03 | 1 | 4945 | 31 | 0 | [6 empty] | 0.0000
140 | 5168 | LINTEL & MULLION CONCRETE | CUM | 31.35 | 31.35 | 139 | 5167 | 4 | 450 | CONCRETE | [5 empty] | 0.0000