## Sheet1
Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA | Project :-SAKAR SCINTILLA
Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE | Selected Group :- CONCRETE
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 5833 | CONCRETE |  | 0.0000 | 0.0000 | 0 | 4888 | 31 | 0 | [6 empty] | 0.0000
2 | 5871 | 4B |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
3 | 6010 | 4B RAFT FOUNDATION M40 | CUM | 8747 | 8747 | 2 | 5871 | 4 | 466 | RAFT FOUNDATION M40 | [5 empty] | 0.0000
4 | 6013 | 4B TRIMIX CUM | CUM | 1832 | 1832 | 2 | 5871 | 4 | 468 | TRIMIX CUM | [5 empty] | 0.0000
5 | 6014 | 4B GRADE SLAB | CUM | 458 | 458 | 2 | 5871 | 4 | 469 | GRADE SLAB | [5 empty] | 0.0000
6 | 6015 | 4B PCC FOR FOUNDATION M15 | CUM | 560 | 560 | 2 | 5871 | 4 | 3 | PCC FOR FOUNDATION M15 | [5 empty] | 0.0000
7 | 6017 | 4B ZARI 7X7 | RFT | 990 | 990 | 2 | 5871 | 4 | 471 | ZARI 7X7 | [5 empty] | 0.0000
8 | 6383 | 4B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 50 | 50 | 2 | 5871 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
9 | 6384 | 4B SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 547 | 547 | 2 | 5871 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
10 | 5973 | 3B |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
11 | 5975 | 3B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 64 | 64 | 10 | 5973 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
12 | 5976 | 3B SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 689 | 689 | 10 | 5973 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
13 | 6394 | 3B BEAM & SLAB M40 (M+L) | CUM | 1068 | 1068 | 10 | 5973 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
14 | 6407 | 3B STAIR M40 (M+L) | CUM | 27 | 27 | 10 | 5973 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
15 | 5834 | 2B |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
16 | 5977 | 2B SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 689 | 689 | 15 | 5834 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
17 | 6393 | 2B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 64 | 64 | 15 | 5834 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
18 | 6395 | 2B BEAM & SLAB M40 (M+L) | CUM | 1068 | 1068 | 15 | 5834 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
19 | 6408 | 2B STAIR M40 (M+L) | CUM | 27 | 27 | 15 | 5834 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
20 | 5835 | 1B |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
21 | 5921 | 1B SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 79 | 79 | 20 | 5835 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
22 | 5980 | 1B SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 849 | 849 | 20 | 5835 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
23 | 6396 | 1B BEAM & SLAB M40 (M+L) | CUM | 1068 | 1068 | 20 | 5835 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
24 | 6409 | 1B STAIR M40 (M+L) | CUM | 45 | 45 | 20 | 5835 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
25 | 5836 | GF |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
26 | 5875 | GF SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 83 | 83 | 25 | 5836 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
27 | 5981 | GF SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 933 | 933 | 25 | 5836 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
28 | 6397 | GF BEAM & SLAB M40 (M+L) | CUM | 1068 | 1068 | 25 | 5836 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
29 | 6410 | GF STAIR M40 (M+L) | CUM | 47 | 47 | 25 | 5836 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
30 | 5837 | 1F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
31 | 5984 | 1F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 30 | 5837 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
32 | 6398 | 1F BEAM & SLAB M40 (M+L) | CUM | 459 | 459 | 30 | 5837 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
33 | 6411 | 1F STAIR M40 (M+L) | CUM | 17 | 17 | 30 | 5837 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
34 | 5838 | 2F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
35 | 5986 | 2F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 34 | 5838 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
36 | 6399 | 2F BEAM & SLAB M40 (M+L) | CUM | 573 | 573 | 34 | 5838 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
37 | 6412 | 2F STAIR M40 (M+L) | CUM | 17 | 17 | 34 | 5838 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
38 | 5839 | 3F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
39 | 5987 | 3F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 38 | 5839 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
40 | 6400 | 3F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 38 | 5839 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
41 | 6413 | 3F STAIR M40 (M+L) | CUM | 17 | 17 | 38 | 5839 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
42 | 5840 | 4F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
43 | 5935 | 4F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 42 | 5840 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
44 | 6401 | 4F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 42 | 5840 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
45 | 6414 | 4F STAIR M40 (M+L) | CUM | 17 | 17 | 42 | 5840 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
46 | 5841 | 5F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
47 | 5938 | 5F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 46 | 5841 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
48 | 6402 | 5F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 46 | 5841 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
49 | 6415 | 5F STAIR M40 (M+L) | CUM | 17 | 17 | 46 | 5841 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
50 | 5842 | 6F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
51 | 5940 | 6F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 50 | 5842 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
52 | 6403 | 6F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 50 | 5842 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
53 | 6416 | 6F STAIR M40 (M+L) | CUM | 17 | 17 | 50 | 5842 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
54 | 5843 | 7F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
55 | 5942 | 7F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 54 | 5843 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
56 | 6404 | 7F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 54 | 5843 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
57 | 6417 | 7F STAIR M40 (M+L) | CUM | 17 | 17 | 54 | 5843 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
58 | 5844 | 8F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
59 | 6385 | 8F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 58 | 5844 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
60 | 6405 | 8F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 58 | 5844 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
61 | 6418 | 8F STAIR M40 (M+L) | CUM | 17 | 17 | 58 | 5844 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
62 | 5845 | 9F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
63 | 6386 | 9F SHEAR WALL / LIFT WALL / COLUMN M55 | CUM | 467 | 467 | 62 | 5845 | 4 | 9 | SHEAR WALL / LIFT WALL / COLUMN M55 | [5 empty] | 0.0000
64 | 6406 | 9F BEAM & SLAB M40 (M+L) | CUM | 569 | 569 | 62 | 5845 | 4 | 477 | BEAM & SLAB M40 (M+L) | [5 empty] | 0.0000
65 | 6419 | 9F STAIR M40 (M+L) | CUM | 17 | 17 | 62 | 5845 | 4 | 478 | STAIR M40 (M+L) | [5 empty] | 0.0000
66 | 5846 | 10F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
67 | 5947 | 10F BEAM, SLAB, STAIR M35 | CUM | 586 | 586 | 66 | 5846 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
68 | 5948 | 10F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 66 | 5846 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
69 | 5847 | 11F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
70 | 5949 | 11F BEAM, SLAB, STAIR M35 | CUM | 586 | 586 | 69 | 5847 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
71 | 5950 | 11F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 69 | 5847 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
72 | 5848 | 12F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
73 | 5951 | 12F BEAM, SLAB, STAIR M35 | CUM | 586 | 586 | 72 | 5848 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
74 | 5991 | 12F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 72 | 5848 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
75 | 5849 | 13F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
76 | 5953 | 13F BEAM, SLAB, STAIR M35 | CUM | 586 | 586 | 75 | 5849 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
77 | 5992 | 13F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 75 | 5849 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
78 | 5850 | 14F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
79 | 5955 | 14F BEAM, SLAB, STAIR M35 | CUM | 586 | 586 | 78 | 5850 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
80 | 5993 | 14F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 78 | 5850 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
81 | 5851 | 15F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
82 | 5957 | 15F BEAM, SLAB, STAIR M35 | CUM | 585 | 585 | 81 | 5851 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
83 | 5994 | 15F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 431 | 431 | 81 | 5851 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
84 | 5852 | 16F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
85 | 5959 | 16F BEAM, SLAB, STAIR M35 | CUM | 586 | 586 | 84 | 5852 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
86 | 5995 | 16F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 84 | 5852 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
87 | 5853 | 17F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
88 | 5961 | 17F BEAM, SLAB, STAIR M35 | CUM | 569 | 569 | 87 | 5853 | 4 | 18 | BEAM, SLAB, STAIR M35 | [5 empty] | 0.0000
89 | 5996 | 17F SHEAR WALL / LIFT WALL / COLUMN M50 | CUM | 467 | 467 | 87 | 5853 | 4 | 10 | SHEAR WALL / LIFT WALL / COLUMN M50 | [5 empty] | 0.0000
90 | 5854 | 18F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
91 | 5997 | 18F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 467 | 467 | 90 | 5854 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
92 | 5998 | 18F BEAM, SLAB & STAIR M30 | CUM | 586 | 586 | 90 | 5854 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
93 | 5855 | 19F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
94 | 5890 | 19F BEAM, SLAB & STAIR M30 | CUM | 586 | 586 | 93 | 5855 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
95 | 5891 | 19F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 467 | 467 | 93 | 5855 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
96 | 5856 | 20F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
97 | 5892 | 20F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 467 | 467 | 96 | 5856 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
98 | 5893 | 20F BEAM, SLAB & STAIR M30 | CUM | 586 | 586 | 96 | 5856 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
99 | 5857 | 21F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
100 | 5894 | 21F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 467 | 467 | 99 | 5857 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
101 | 5895 | 21F BEAM, SLAB & STAIR M30 | CUM | 586 | 586 | 99 | 5857 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
102 | 5858 | 22F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
103 | 5896 | 22F BEAM, SLAB & STAIR M30 | CUM | 586 | 586 | 102 | 5858 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
104 | 5897 | 22F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 467 | 467 | 102 | 5858 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
105 | 5859 | 23F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
106 | 5898 | 23F BEAM, SLAB & STAIR M30 | CUM | 586 | 586 | 105 | 5859 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
107 | 5899 | 23F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 467 | 467 | 105 | 5859 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
108 | 5860 | 24F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
109 | 5900 | 24F BEAM, SLAB & STAIR M30 | CUM | 665 | 665 | 108 | 5860 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
110 | 5901 | 24F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 576 | 576 | 108 | 5860 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
111 | 5861 | 25F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
112 | 5902 | 25F BEAM, SLAB & STAIR M30 | CUM | 462 | 462 | 111 | 5861 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
113 | 5999 | 25F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 394 | 394 | 111 | 5861 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
114 | 5862 | 26F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
115 | 5904 | 26F BEAM, SLAB & STAIR M30 | CUM | 457 | 457 | 114 | 5862 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
116 | 6000 | 26F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 394 | 394 | 114 | 5862 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
117 | 5863 | 27F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
118 | 5906 | 27F BEAM, SLAB & STAIR M30 | CUM | 457 | 457 | 117 | 5863 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
119 | 6001 | 27F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 394 | 394 | 117 | 5863 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
120 | 5864 | 28F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
121 | 5908 | 28F BEAM, SLAB & STAIR M30 | CUM | 457 | 457 | 120 | 5864 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
122 | 6002 | 28F SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 397 | 397 | 120 | 5864 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
123 | 5865 | 28F |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
124 | 5886 | TF |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
125 | 5966 | TF BEAM, SLAB & STAIR M30 | CUM | 470 | 470 | 124 | 5886 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
126 | 5967 | LINTEL & MULLION |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
127 | 5968 | LINTEL & MULLION CONCRETE | CUM | 292.5 | 292.5 | 126 | 5967 | 4 | 450 | CONCRETE | [5 empty] | 0.0000
128 | 6005 | OH |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
129 | 6006 | OH SHEAR WALL / LIFT WALL / COLUMN M40 | CUM | 165 | 165 | 128 | 6005 | 4 | 12 | SHEAR WALL / LIFT WALL / COLUMN M40 | [5 empty] | 0.0000
130 | 6007 | OH BEAM, SLAB & STAIR M30 | CUM | 223 | 223 | 128 | 6005 | 4 | 19 | BEAM, SLAB & STAIR M30 | [5 empty] | 0.0000
131 | 6008 | WALLS |  | 0.0000 | 0.0000 | 1 | 5833 | 31 | 0 | [6 empty] | 0.0000
132 | 6009 | WALLS SHEAR WALL / LIFT WALL / COLUMN M35 | CUM | 1217 | 1217 | 131 | 6008 | 4 | 13 | SHEAR WALL / LIFT WALL / COLUMN M35 | [5 empty] | 0.0000